## FMEA
Function | Potential Failure Mode(s) | Potential Technical Effect(s) of Failure | Potential Business Consequence(s) of Failure | Sev | Potential Cause(s)/ Mechanism(s) of Failure | Prob | Current Controls |  | Det | RPN | Recommended Controls |  | Responsibility & Target Completion Date | Action Results
[14 empty] | Implemented Controls |  | New Sev | New Occ | New Det | New RPN
[7 empty] | Preventive Controls | Detective Controls |  |  | Preventive Controls | Detective Controls |  | Preventive Controls | Detective Controls
Import (outside of application) | File can’t be imported | Data not updated to expected values | Charge information is out-of-date | 8 | Export file not saved | 3 | None | None | 8 | 192 | Allow user to choose which set of charge types to export Allow user to reexport | Log that file was export, include who and what and when
Import | Reconciliation error - identifying an exported charge as matching the incoming record | Data inconsistency | Charge information in is unable to be updated to reflect current state | 3 | Someone modified export file prior to importing into in such a way that can no longer identify the records as being the same | 8 | None | None | 8 | 192 | Prohibit importing anything with a Number that matches a currently exported charge, Consider implementing a fuzzy match that makes suggestions about potential matches | Log that there is an exported charge with this number but they are not considered equal
Import (outside of application) | File can’t be imported | Data in not updated to expected values | Charge information is out-of-date | 8 | Someone has modified the exported file | 8 | None | None | 1 | 64 | Implement tools which remove the need for a person to modify the file manually.
Import | Bad data in file - successfully imported | Data inconsistency | Charge information in is unable to be updated to reflect current state, Erroneous data | 5 | Someone modified file | 1 | None | Human inspection | 8 | 40 | Implement tools which remove the need for a person to modify the file manually. Use API. | Log who, what, when - log when an exported charge is set to active/inactive
Export (outside of application) | Export worked - file not correct | File is created but not importable | Charge information in is unable to be updated to reflect current state | 5 | Unknown | 1 | None | Human inspection | 5 | 25 | Use API instead of files.
Import | Import not performed | Data not updated | Charge information in is unable to be updated to reflect current state | 3 | File not sent to admin to import, admin doesn’t do import, miscommunication | 1 | None | None | 8 | 24 |  | Have an alert on application that indicates time since last import
Import (outside of application) | File can’t be imported | Data in not updated to expected values | Charge information is out-of-date | 8 | Rules changed | 2 | Update to required for this to occur | Change log | 1 | 16 | Thoroughly test any updates to in test and stage environment in concert with application. | log errors related to reading file
Export | Charge doesn’t have a Number | Export can’t identify “current” charge to compare to | Work stoppage | 8 | User didn’t input | 1 | None | None | 1 | 8 | Prohibit charge from reaching completed state without Number
User login | Active Directory inaccessible | User can’t login | Work stoppage | 8 | Connectivity | 1 | Unknown | Alerts | 1 | 8
Anywhere | Database unreachable | Application will cease to function | Work stoppage | 8 | Connectivity | 1 | Unknown, possibly alerts | Alerts | 1 | 8
Import (outside of application) | File can’t be imported | Data in not updated to expected values | Charge information is out-of-date | 8 | Export was errant | 1 | Code would have to be modified for this to happen | None | 1 | 8
General usage | Inaccessible | Can’t access the site at all | Work stoppage | 8 | Connectivity | 1 | Redundancy | Alerts | 1 | 8
Import | File can't be parsed properly | Data not updated | Charge information in is unable to be updated to reflect current state | 3 | Someone modified file | 2 | None | someone admitting to editing file | 1 | 6
Import | File parsed but records can’t be mapped to charges properly | Records not created | Charge information in is unable to be updated to reflect current state | 3 | Someone modified file | 2 | None | someone admitting to editing file | 1 | 6
General usage | Browser compatibility | Display problems | Possibly undesirable user experience, worst case is work stoppage | 3 | Old browser, some library not compatible | 2 | Standard browser usage (IE11) | None | 1 | 6
Export (outside of application) | Export didn’t work | Data in is not reconciled | Charge information in is unable to be updated to reflect current state | 5 | Unknown | 1 | None | None | 1 | 5 |  | Log during reconciliation
Import | Reconciliation error - identifying an exported charge as matching the incoming record | Data inconsistency | Charge information in is unable to be updated to reflect current state | 3 | Error in equality comparison method | 1 | Code would have to be modified | Unit tests | 1 | 3
Import | File can't be parsed properly | Data not updated | Charge information in is unable to be updated to reflect current state | 3 | Export didn’t work properly | 1 | None | Human inspection | 1 | 3
Import | File parsed but records can’t be mapped to charges properly | Records not created | Charge information in is unable to be updated to reflect current state | 3 | Export didn’t work properly | 1 | None | Human inspection | 1 | 3
Import | File parsed but records can’t be mapped to charges properly | Records not created | Charge information in is unable to be updated to reflect current state | 3 | Classification records in database not setup properly | 1 | Can only be changed with database access | None | 1 | 3
Note on A3: bala: List down the fucntion or purpose of the asset. If more than one purpose is identified for the identified service list them down separately
Note on B3: bala: In what all ways the service running on this asset can fail? ie the vulnerabilities List down each failure mode separately
Note on C3: bala: if the vulnerability happens, then what could be the effect of the failure? If there is more than one failure list them seperately
Note on E3: bala: Refer Severity Table
Note on F3: bala: What are the cause(s) of this Failure? List down causes for every failure. Each failure can have more than one cause
Note on G3: bala: Refer Probabilty Table
Note on H3: bala: Identify the current controls vis a vis preventive and detective controls. If there are more than one, then list them separately
Note on J3: bala: Refer Detection table
Note on L3: bala: What are the controls recommended to reduce the RPN number? If more than one control, thn list them separately.
Note on N3: bala: Specify the responsibility & target date to implement the identified control(s)
Note on O4: bala: Specify which control was implemented? If more than one control was implemented for the identified single cause then list them separately.

## Other failures worth noting
Function | Potential Failure Mode(s) | Potential Technical Effect(s) of Failure | Potential Business Consequence(s) of Failure | Sev | Potential Cause(s)/ Mechanism(s) of Failure | Prob | Current Controls |  | Det | RPN | Recommended Controls |  | Responsibility & Target Completion Date | Action Results
[14 empty] | Implemented Controls |  | New Sev | New Occ | New Det | New RPN
[7 empty] | Preventive Controls | Detective Controls |  |  | Preventive Controls | Detective Controls |  | Preventive Controls | Detective Controls
TBD | registration with testflight | [8 empty] | 0
| device loss/theft | physicial absence | compliance, data loss, work stoppage | 8 | accident, neglect, fraud | 1 | hiring processes vet people |  |  | 0
sync | too long since sync | bad data | compliance | 8 | accumulated failures |  | educate users |  |  | 0
sync | user has restored old data from a phone backup | [8 empty] | 0
| revoked authentication |  | work stoppage | [6 empty] | 0
0
0
0
0
Note on A2: bala: List down the fucntion or purpose of the asset. If more than one purpose is identified for the identified service list them down separately
Note on B2: bala: In what all ways the service running on this asset can fail? ie the vulnerabilities List down each failure mode separately
Note on C2: bala: if the vulnerability happens, then what could be the effect of the failure? If there is more than one failure list them seperately
Note on E2: bala: Refer Severity Table
Note on F2: bala: What are the cause(s) of this Failure? List down causes for every failure. Each failure can have more than one cause
Note on G2: bala: Refer Probabilty Table
Note on H2: bala: Identify the current controls vis a vis preventive and detective controls. If there are more than one, then list them separately
Note on J2: bala: Refer Detection table
Note on L2: bala: What are the controls recommended to reduce the RPN number? If more than one control, thn list them separately.
Note on N2: bala: Specify the responsibility & target date to implement the identified control(s)
Note on O3: bala: Specify which control was implemented? If more than one control was implemented for the identified single cause then list them separately.